## Sheet1
Dear Mr. Quyet, Mr. Trung
I’m writing to present daily report of Group 1 30/01/2019). Thanks for your attention!
| Daily Report on | 30/1/2019
| Team members | VSSon | VVDong | PTPhuong3 | NTMDuyen | NDVan | NTHung | LVCHai2
| Plan | Create Prototype | Create Prototype | Create Prototype | Create Prototype | Create Prototype | Create Prototype | Create Prototype
|  | Create Test Case | Create Test Case | Create Test Case | Create Test Case | Create Test Case | Create Test Case | Create Test Case
|  | Create Q&A | Create Q&A | Create Q&A | Create Q&A | Create Q&A | Create Q&A | Create Q&A
| Actual | Create Prototype | Create Prototype | Create Prototype | Create Prototype | Create Prototype | Create Prototype | Create Prototype
|  | Create Test Case | Create Test Case | Create Test Case | Create Test Case | Create Test Case | Create Test Case | Create Test Case
|  | Create Q&A | Create Q&A | Create Q&A | Create Q&A | Create Q&A | Create Q&A | Create Q&A
|  | Update Template Admin Angular | Update Template Admin Angular | Update Template Admin Angular | Update Template Admin Angular | Update Template Admin Angular | Update Template Admin Angular | Update Template Admin Angular
Edit Database
| Status and % execute/plan | Complete | Complete | Complete | Complete | Complete | Complete | Complete
| Output | https://drive.google.com/drive/folders/1PBGtcmbyEOQkdO9fJvq9AdQaQN4lvW_4?fbclid=IwAR1Hl6QK7_axlb8NwMxh4zfls1v_c0WzGTw2LHb0mLw8dzQdyXNP8XcXPO0
| Issue | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Action | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Next Plan | Code Front end follow diagram | Code Front end follow diagram | Code Front end follow diagram | Code Front end follow diagram | Code Front end follow diagram | Code Front end follow diagram | Code Front end follow diagram
| Team’s Progress | Group progress: Complete
======================================================================================